## Sheet 1
| Name | Target | Achievement
Development of Chhat ghats
output-219 | Number of permanent Chhat ghats constructed | 37 | 39
output-221 | Number of temporary Chhat ghats constructed | 593 | 598
outcome-216 | % age of projects COMPLETED within deadline as per Work Order | 100 | 101
outcome-218 | % age of projects COMPLETED within deadline as per Work Order | 100 | 102
Major Drainage
output-161 | Total number of machines procured and made operational | 59 | 65
output-163 | Total length of drains (km) desilted using machinery | 382 | 66
output-165 | Total production of silt (in Lakhs MT) | 4.84 | 67
output-167 | Number of staff engaged in desilting | 167 | 68
outcome-186 | Quantity of silt disposed at SLF site (in Lakhs MT) | 1.16 | 69
outcome-188 | Quantity of silt disposed at banks as well in depression (in Lakhs MT) | 3.68 | 70
outcome-190 | Silt used in productive activity | 0 | 2
Major Drainage (b) Embankment/ Major Drainage Schemes
output-169 | Number of projects including ongoing projects of previous years | 1 | 2
output-171 | Number of projects for which construction has started/in progress | 1 | 3
output-173 | Number of projects for which construction is fully completed | 1 | 4
outcome-192 | % age of ONGOING projects that are within deadline as per Work Order | 100 | 5
outcome-194 | % age of projects COMPLETED within deadline as per Work Order | 100 | 6
outcome-196 | Number of projects where penalty imposed on the contractor due to delay in completion. | 100 | 7
Other Drainage Works
output-175 | Number of projects including ongoing projects of previous years | 15 | 25
output-177 | Number of projects for which construction has started/in progress | 15 | 26
output-179 | Number of projects for which construction is fully completed | 10 | 27
output-181 | Length of projects which have been completed (in kms) | 35.7 | 28
output-186 | Date of completion of work | 29.02.2020
output-188 | Percentage of work completed | 100 | 102
output-190 | Number of projects including ongoing projects of previous years | 33 | 35
output-192 | Number of projects for which construction has started/in progress | 33 | 35
output-194 | Number of projects for which construction is fully completed | 20 | 36
output-195 | Date of Tender floating | 27.05.19 | 28.06.19
output-196 | Date of work award | 27.07.19 | 29.06.19
output-197 | Date of Start of work | 12.08.19 | 13.05.19
output-198 | Date of completion of work | 11.08.20
output-199 | Percentage of work completed | 30
output-200 | Date of Tender floating | 27.05.19
output-201 | Date of work award | 27.07.19 | 28.05.20
output-202 | Date of Start of work | 12.08.19 | 28.05.19
output-203 | Date of completion of work | 11.08.20 | 12.09.20
output-204 | Percentage of work completed | 50 | 53
output-205 | Date of Tender floating | -
output-206 | Date of work award | 27.05.19
output-207 | Date of Start of work | 11.06.19
output-208 | Date of completion of work | 10.06.20
output-209 | Percentage of work completed | 25 | 28
output-211 | Number of projects including ongoing projects of previous years | 7 | 29
output-213 | Number of projects for which construction has started/in progress | 7 | 30
output-215 | Number of projects for which construction is fully completed | 7 | 31
output-217 | Length of projects which have been completed (in kms) | 20.98 | 32
outcome-198 | % age of ONGOING projects that are within deadline as per Work Order | 100 | 33
outcome-200 | % age of projects COMPLETED within deadline as per Work Order | 100 | 102
outcome-202 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 103
outcome-204 | % age of ONGOING projects that are within deadline as per Work Order | 100 | 104
outcome-206 | % age of projects COMPLETED within deadline as per Work Order | 100 | 105
outcome-208 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 106
outcome-210 | % age of ONGOING projects that are within deadline as per Work Order | 100 | 107
outcome-212 | % age of projects COMPLETED within deadline as per Work Order | 100 | 102
outcome-214 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 3
Rejuvnation of Drains
output-226 | Number of drains including ongoing projects of previous years | 27 | 29
output-227 | Number of drains for which construction has started/in progress | 10 | 30
output-228 | Number of drains for which construction is fully completed | 2 | 31
output-229 | % of physical work completed | 7 | 32
output-230 | Number of Minors including ongoing projects of previous years | 5 | 33
output-231 | Number of Minors for which construction has started/in progress | 5 | 34
output-232 | Number of Minors for which construction is fully completed | 1 | 35
output-233 | % of physical work completed | 5 | 36
output-234 | Date of appointment of consultant | NA
output-235 | Date of receipt of DPR | 10.07.2019 | 10.12.2019
output-236 | Date of Tender floating | 01.01.2020 | 10.12.2020
output-237 | Date of work award | 15.02.2020 | 10.12.2021
output-238 | Date of Start of work | 15.03.2020 | 10.12.2022
output-239 | Date of completion of work | 31.12.2020 | 10.12.2023
output-240 | Percentage of work completed | 5 | 10
outcome-226 | % age of ONGOING drains that are within deadline as per Work Order | 100 | 11
outcome-228 | % age of drains COMPLETED within deadline as per Work Order | 100 | 12
outcome-230 | Number of drains where penalty imposed on the contractor due to delay in completion. | 0 | 13
outcome-232 | Total length of Drainsthat rejuvented (In Km) | 18.73 | 14
outcome-234 | % age of ONGOING Minors that are within deadline as per Work Order | 100 | 105
outcome-236 | % age of Minors COMPLETED within deadline as per Work Order | 100 | 106
outcome-238 | Number of Minors where penalty imposed on the contractor due to delay in completion. | 0 | 107
outcome-240 | Total length of Minors that rejuvented (In Km) | 3.4 | 108
Rejuvnation/ maintenance & preservation of water bodies
output-222 | Number of water bodies including ongoing projects of previous years | 95 | 98
output-223 | Number of water bodies for which construction has started/in progress | 48 | 99
output-224 | Number of water bodies for which construction is fully completed | 20 | 100
output-225 | Percentage of work completed | 25 | 101
outcome-220 | % age of ONGOING water bodies that are within deadline as per Work Order | 100 | 102
outcome-222 | % age of water bodies COMPLETED within deadline as per Work Order | 100 | 103
outcome-224 | Number of water bodies where penalty imposed on the contractor due to delay in completion. | 0 | 104