## UD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Swachh Bharat Mission (SBM) (Rs.13000 Lakh) (R- Rs.1300 Lakh C- Rs.11700 Lakh) | a) To make the city Open Defecation Free (ODF) | Number of toilets seats newly constructed in Community Toilets (through DUSIB) | 1050 | 1385 | 1385 |  | Number of people provided access to toilet | 42000 | 55400 | 55400 |  | The indicator "Number of Toilet seats newly constructed in Community Toilets and Public Toilets" by various executing agencies may not be required to reflect in Outcome Budget 2019-20 as our entire focus is on attaining and sustaining ODF status for ULBs. Municipal agencies have not sent the target of Individual Household Toilet (IHHT) seats and they have not any requirement under this component. Further, agencies have not sent the proposal of PTs/CTs that can be constucted from the IHHT fund as per Ministry guidelines. Hence, indicators "Number of Toilet seats newly constructed in Community Toilets and Public Toilet" by various executing agencies may be omitted/deleted
|  |  | Number of toilets seats newly constructed in Community Toilets (through North DMC) | NR | NR |  |  | Number of people provided access to toilet | NR | NR
|  |  | Number of toilets seats newly constructed in Community Toilets (through South DMC) | NR | NR |  |  | Number of people provided access to toilet | NR | NR
|  |  | Number of toilets seats newly constructed in Community Toilets (through East DMC) | 90 | 90 |  |  | Number of people provided access to toilet | 6000 | 6000
|  |  | Number of toilets seats newly constructed in Public Toilets (through East DMC) | 623 | 776 |  |  | Number of people provided access to toilet | 13000 | 18100
|  |  | Certified Open Defecation free (ODF) city | 2 | 5 | 4 | 5 | Number of wards declared Open Defecation Free | 22 | 294 | 190 | 294
|  | b) Modern and Scientific Solid waste management through local bodies | Additional installation capacity added from Waste to Energy plants (MW) | 0 | 1 | 0 | 1 | Additional solid waste processed per day (MTPD) | 0 | 2500 | 0 | 2500 | Subject to release of SBM Fund from MoHUA, GoI as Rs 125.00 crore is approved for this plant. Only Rs 53.12 crore has been received so far.
2 | Atal Mission For Rejuvenation & Urban Transformation (AMRUT) (Rs.15000 Lakh) (Capital) | a) To increase access of households to water network | Number of projects sanctioned for water | 8 | 8 | 8 | 8 | [5 empty] | 03 Water supply projects of DJB in EDMC shall be completed to the extent of 100%. The water projetcs will be completed partially during 2017-18, the achievements of water projects shall be completed in by 2018-19
|  |  | Number of projects completed | 3 | 5 | 3 | 5 | % of projects completed within timeline mentioned in work order | 3 | 5 | 100% | 100%
|  |  | Length of water lines laid (in KM) | 140 | 150 | 140 | 150 | Number of colonies connected through water pipelines | 3 | 4 | 3 | 4
[8 empty] | Total number of households benefited | 45000 | 50000 | 45000 | 50000
|  | b) To increase access of households to sewerage network | Number of projects sanctioned for Sewerage | 5 | 5 | 5 | 5
|  |  | Number of work has been awarded | 3 | 6 | 4 | 5 | [5 empty] | One project of kilkori SPS is yet to be awarded
|  |  | Number of projects completed | 0 | 0 | 0 | 0 | % of projects completed within timeline mentioned in work order | 0 | 0 | 0 | 20 | All the 04 projects of laying sewer network have been awarded. Date of Completion - one project-July, 2019, two projects-Jan. 20 & Nov. 20 and one project- Dec. 2021. After completion of projects 75000 households will be having acess to sewerage facilities. One project is for rehabilitation of Kilkori Sewerage Pumping Station. Tenders have been invited.
|  |  | Length of sewer lines laid (in KM) | 14 | 100 | 64 | 100 | Number of colonies connected through sewer lines | 0 | 0 | 0 | 0
[8 empty] | Total number of households benefited | 0 | 0 | 0 | 0
|  | c) To augment sewage treatment capacity | Treatment capacity added of sewage /septage (in MGD) | 0 | 0 | 0 | 0 | % of projects completed within prescribed time line | NA | NA | 0 | 0 | 01 project of upgradation of 10 MGD Yamuna Vihar Ph-II STP is being undertaken. The concultant are being appointed.
|  |  | Number of projects sanctioned | 1 | 1 | 1 | 1
|  |  | Number of projects completed | 0 | 0 | 0 | 0
|  | d) To develop kachcha walkways alongwith fitness stations comprising of different fitness levels (South DMC) | No of paved pathways proposed | 3 | 17 | 8 | 8 | No. of Households / colonies benifitted | 150 | 850 | 350 | 500 | Project cost Rs 4 crore and 1st installment of Rs 80 lacs was received and the UC of Rs 75.41 lakh (94.26 %) was submitted. The second installment is awaited.
|  | e) Enhancing amenity value of cities by creating and upgrading green sapces,parks and recreation centres, especially for children (South DMC) | No. of green parks to be strengthened by installing children play equipments | NA | 35 | 2 | 4 | No. of Households / colonies benifitted | 0 | 1750 | 1300 | 1700 | Project cost 2.70 Cr. Newly designed fibre made Children Play Equipments of good quality will be installed. Work is in progress. 1st installment of Rs 54 lakh was received and UC of Rs 40.85 lakh(75.6%)has been submitted.
|  | F) Enhancing amenity value of cities by creating and upgrading green sapces,parks and recreation centres, especially for children (East DMC) | No. of green parks to be strengthened by installing children play equipments | 95 | 150 | 36 | 111 | No. of Households / colonies benifitted | 256 | 430 | 95 | 291 | Total cost of scheme Rs 10 crore total allocation amount Rs 1.99 crore
|  | g) Rejuvenation of Shahdara Jheel by treating waste / storm water through treatment plant by Phytorid technology by East DMC | % of work completed | NA | 70 | NA | 70 | [5 empty] | Project cost of Rs 15 crore, Lake Development completion: DEC. 19, Landscaping and Horticulture completion: September 19.
|  | h) Faecal sludge management generated from existing community toilet complexes and MC primary school toilets by treating waste through treatment technology of sludge and liquid waste by BIOMAD technology in East DMC areas | % of work completed | NA | 70 | NA | 70 | [5 empty] | Project cost of Rs.44.13 crore Present status: Date of Tender: June, 2019 Date of Start: July, 2019 Date of completion: March, 2020 (Tentative)
[8 empty] | No of CTC covered | NA | 50 | NA | 9
[8 empty] | No of primary school covered | 0 | 20 | 0 | 0
[8 empty] | IHHL | 0 | 17 | 0 | 0
3 | Smart City-NDMC (Rs.5000 Lakh) (Capital) | Improvement in specific socio-economic indicators of smart cities based on the specific development theme | Number of Rooftop Solar Panel on NDMC buildings installed | 110 | 272 | No roof space available on NDMC buildings |  | Solar Energy generated in KWH/Day | 3453 | NR | 10815 units/day |  | No roof space available on NDMC buildings
|  |  | Number of Smart Toilets constructed | 54 | 218 | 70 | 109 | Average number of beneficiaries using the smart toilet daily | NR | NR | 500 | 550
|  |  | Number of Giant Smart Digital Screens installed | 3 | [5 empty] | Work has been completed
|  |  | Number of vehicles transporting garbage fitted with GPS | 43 | 50 | 63 |  | Average time taken per vehicle for disposal of waste (Hour) | 3 | 3 | 3 |  | Work has been completed.
|  |  | Number of Smart Class Rooms | 444 | 777 | 444 | 805 | Number of students using smart classes | 14834 | 14900 | 12846 | 12328 | Around 361 are to be set up in primary sections for which tender is to be issued
|  |  | Installation of Water ATMs (no.) | 17 | 20 | 37 | 77 | Number of parks to be covered by Water ATMs | 5 | 8 | NR
[8 empty] | Avaerage Liters of water consumed by public through these water ATM |  |  | 518 | 1000
|  |  | Number of public bikes deployed |  |  | 400 | 500 | Avergae Numbers of users on a daily basis |  |  | 350 | 600
|  |  | Number of Atal tinkering Labs |  |  | 3 | 10 | Number of Student benificairies |  |  | 1700
|  |  | Number of student tarined and assesed in Skill Centre at Mandir Marg |  |  | 1086 | 1500 | Number of students placed |  |  | 669 | 1000
|  |  | Number of location with sensor based parking |  |  | 84 | 124 | Monthly revenue through sensor based parking (Rs in lakh) |  |  | 76 | 110.5 | Phase 1: Location =84, Revenue monthly=75 Lakh, Phase-II:location=40,Revenue Monthly=34.50 Lakh
4 | National Urban Livelihood Mission (Rs.1500 Lakh) (Revenue) | a) Self Employment Programme (SEP): Financial assistance in the form of interest subsidy on the bank loan over and above 7% rate of interest for setting up of single or group enterprise. | Number of District Task Force Committees constituted | 11 | 0 | 0 | 0 | Scrutiny and sanction of recommended loans under SEP (No of applications). | 0 | 620 | 0 | 620
[8 empty] | Number of Individual enterprises funded under Self Employment Programme (SEP) | 0 | 500 | 0 | 500
[8 empty] | Number of Group enterprises funded under Self Employment Programme (SEP) | 0 | 120 | 0 | 120
|  | b) Social Mobilisation & Institution Development i/c formation of City Livelihood Centres (CLCs) where urban poor can offer their goods & services in organized manner to potential buyer | Number of Resource Organisations (ROs) with which MoU is signed | 22 | 20 | 0 | 20 | Number of women empowered through SHG formation | 75 | 8000 | 216 | 8000
|  |  | Number of SHGs formed by ROs | 7 | 800 | 18 | 800 | Number of meetings conducted by SHGs | 15 | 800 | 36 | 800
|  |  | Number of workshops held for Financial Literacy among SHG beneficiaries | 0 | 150 | 0 | 150 | Number of beneficiaries empowered through Financial Literacy workshops | 0 | 1500 | 0 | 1500
|  |  | Number of CLCs established | 0 | 0 | 0 |  | Total sales / trade taking place through CLCs (Rs lakhs) | 0 | 0 | 0
|  | c) Employment though skill training and Placement: Provide training through State Training Providers (STPs) and linking them to employment. | Number of proposals received for State Training Providers (STPs) | 35 | 15 | 64 | 15 | Number of people enrolled for training | 60 | 2500 | 1830 | 2500 | Expression of interest is being invited from the NSDC partners by way of advertisements.
|  |  | Number of proposals approved for STPs | 9 | 10 | 4 | 10 | Number of People completed the trainning with certification | 0 | 4300 | 0 | 4300 | Assessement tests have been conducted for 3 batches (90 beneficiaries). Result is awaited
|  |  | Number of proposed trades for trainings by STPs | 15 | 20 | 15 | 20 | Number of trainees engaged in full-time wage employment within 3 months of course completion | 0 | 3010 | 0 | 3010 | Job Roles:- 1. House Keeping 2. Pedicure & Menicure 3.Food & Beverage 4. Insurance Sales Advisor 5.General Duty Attendant 6. Filed Technician Computing & Periferals 7. Self Employed Tailor 8. Consignment Booking Assistant 9. Make-up Artist 10.Tailor/Basic Sewing Operator 11.Assistant Fashion Sales & Showroom Representatives 12. Sales Assistant 13. Domestic data Entry Operator 14. Account Assistant using Tally 15. Hand Embroidery Gardener
[8 empty] | Number of trainees engaged in self-employment within 3 months of course completion | 0 | 1290 | 0 | 1290
|  | d) Shelter for urban homeless | Number of new Night Shelters constructed | 0 | 1 | 2 | 2 | Total capacity added at Night Shelters | 0 | 250 | 500 | 500 | 2 works of last year could not be completed in absence of release of fund
|  |  | Number of Night Shelters newly taken up for refurbishment | 8 | 13 | 11 | 13 | Total capacity added at Night Shelters | 1000 | 960 | 1960 | 1960
5 | Augmentation of infrastructure i.e. Road, Streets, Street light, Local Parks etc. (MLALAD) (Rs.80000 Lakh) (Capital) | Carry out development work in each Assembly Constituency on the recommendation of Hon'ble MLAs | Projects carried over from previous year | 44 | 250 | 310 | 3380
|  |  | Number of projects newly sanctioned | 452 | 400 | 3344 | 2500 | Number of projects where construction work started | 974 | 650 | 686 | 2400
[8 empty] | Number of projects where works completed | 724 | 600 | 274 | 1200
[8 empty] | % of projects completed within prescribed time line as per work order | 51% | 60% | 65% | 60%
[8 empty] | % of projects where Third Party Quality (TPQ) control done | 93% | 60% | 67% | 70%
[8 empty] | % of projects found satisfactory in TPQ control | 100% | 90% | 66% | 100%
6 | Provision of essential services in unauthorized colonies (Rs 100000 Lakh) (R- Rs.500 Lakh C- Rs. 99500 Lakh) | a) Carrying out works related to shifting of HT/LT line etc. through Power Deptt. | Number of works sanctioned for shifting of HT/LT lines (Power Department) | 6 | 10 | 13 | 10
|  |  | Number of projects where shifting work started | 9 | 10 | 13 | 10 | [5 empty] | Work in process of two spillover schemes of 2017-18
|  |  | Number of projects where works completed | 9 | 10 | 3 | 10 | Total number of Colonies benefited | 11 | 15 | 8 | 15
[8 empty] | % of projects completed within prescribed time line as per work order | 78% | 100% | 75% | 100%
|  | b) Providing basic Amenities such as Roads & S.W. drains, through DSIIDC | Number of projects sanctioned for construction of road (DSIIDC) | 98 | 40 | 150 | 35 | [5 empty] | Target was fixed as per the availability of funds as on April, 2019
|  |  | Number of projects where construction work started | 108 | 59 | 136 | 49
|  |  | Number of projects where works completed | 164 | 164 | 92 | 197 | Total number of Colonies benefited | 132 | 120 | 115 | 120
[8 empty] | % of projects completed within prescribed time line as per work order | 50 | 100% | 50% | 100%
|  |  | Total length of roads added through completed projects (in KM) | 529 | 395 | 589 | 1261 | % of projects for which third party quality (TPQ) control done | 100 | 100% | 100% | 100%
[8 empty] | % of projects found satisfactory in TPQ | 100 | 100% | 100 | 100%
|  |  | Number of projects sanctioned for construction of drains | 98 | 40 | 150 | 35 | [5 empty] | Target was fixed as per the availability of funds as on April, 2019
|  |  | Number of projects where construction work started | 108 | 59 | 136 | 49
|  |  | Number of projects where works completed | 164 | 164 | 92 | 197 | Total number of Colonies benefited | 132 | 120 | 115 | 120
[8 empty] | % of projects completed within prescribed time line as per work order | 50 | 100% | 50% | 100%
|  |  | Total length of drains added through completed projects (in KM) | 953 | 790 | 1178 | 2522 | % of projects for which third party quality (TPQ) control done | 100 | 100% | 100% | 100%
[8 empty] | % of projects found satisfactory in TPQ | 100 | 100% | 100% | 100%
|  | c) Providing basic Amenities such as Roads & S.W. drains, through (I&FC) | Number of projects sanctioned for construction of road ( I&FC) |  | NR | 511 | 171
|  |  | Number of projects where construction work started |  | NR | 372 | 201
|  |  | Number of projects where works completed |  | NR | 5 | 644 | Total number of colonies benefited |  | NR | NR | 523
[8 empty] | % of projects completed within prescribed time line as per work order |  | NR | NR | 100
|  |  | Total length of roads added through completed projects (in KM) |  | NR | 121 | 1397 | % of projects for which third party quality (TPQ) control done |  | NR | NR | 100
[8 empty] | % of projects found satisfactory in TPQ |  | NR | NR | 100
|  |  | Number of projects sanctioned for construction of drains |  | NR | 377 | 108
|  |  | Number of projects where construction work started |  | NR | 270 | 209
|  |  | Number of projects completed for drains |  | NR | 3 | 481 | Total number of Colonies benefited |  | NR | NR | 523
[8 empty] | % of projects completed within prescribed time line as per work order |  | NR |  | 100
|  |  | Total length of drains added through completed projects (in KM) |  | NR | 69 | 2037 | % of projects for which third party quality (TPQ) control done |  | NR | NR | 100
[8 empty] | % of projects found satisfactory in TPQ |  | NR | NR | 100
7 | Trans Yamuna Area Development (Rs.10000 Lakh) (Capital) | Development work in Trans Yamuna Area | Projects carried over from previous year |  |  | 49 | 196
|  |  | Number of projects newly sanctioned | 49 | 30 | 229 | 60 | Number of works started | NA | 49 | 78 | 151
[8 empty] | Number of projects where work completed | NA | 38 | 33 | 196
[8 empty] | % of projects completed within prescribed time line as per work order | NA | 100 | 100 | 100
[8 empty] | % of projects where Third Party Quality (TPQ) control done |  |  | 80 | 100
[8 empty] | % of projects found satisfactory in TPQ control |  |  | 75 | 90
|  | Critical |  |  | Critical
|  | Green |  |  | Green
|  | Red |  |  | Red
|  | NA |  |  | NA
|  | Total |  |  | Total
8 | Provision of Essential services in Unauthorized colonies-CRF-DSIIDC (Rs.1060 Lakh) (Capital) (Rs.10000 Lakh) (Capital) | Providing basic Amenity of Roads through DSIIDC | Length of New Road Constructed in unauthorized colonies (KM) | NA | NR |  |  | Total Number of Unauthorised colonies covered | NA | NR
[8 empty] | Number of Household benefirted in Unauthorized colonies | NA | NR
8 | Market Development fund (Rs 5000 Lakh) (Revenue) | Providing basic infrastructure in various Market areas | Number of Proposal received | NA | NR |  |  | No of Market covered | NA | NR |  |  | The guidelines/SOP of the Market Development Fund is under preparation.
|  |  | Numer of Projects where work started | NA | NR
|  |  | Number of projects where works completed | NA | NR |  |  | % of projects completed within prescribed time line as per work order | NA | NR
9 | Mukhyamantri Sadak Punrothhon Yojana (Rs 80000 Lakh) (Capital) | Improvement of dilapidated roads and lanes and other works by DMCs | Projects carried over from previous year |  |  | 0
|  |  | Number of projects newly sanctioned |  |  | 399 |  | Number of works started |  |  |  |  | Agencies execute the schemes are DMCs, PWD, I&FC, DUSIB and DSIIDC. Break-up of work sanction to executing agencies are: I&FC: 29; PWD: 3; North DMC: 132; South DMC: 5; East DMC: 229; New Delhi MC: 1.
[8 empty] | Number of projects where work completed |  | NR
% of projects completed within prescribed time line as per work order
% of projects where Third Party Quality (TPQ) control done
% of projects found satisfactory in TPQ control