## Blank_Format (hidden)
Department Name…………………………………………………………..
Sr. No | Name of the Scheme / Programme | Budget Allocation (Rs. Lakhs) | Expr. upto June 2017 | Timelines | Objectives | OUTPUTS | [7 empty] | OUTCOMES | [7 empty] | Remarks | Risk Factors
[6 empty] | Indicator | Baseline 2016-17 | Target 2017-18 | Target Apr-June 2017 | Achievement Apr-Jun 2017 | Target Apr-Sep 2017 | Target Apr-Dec 2017 | Target 2017-18, if revised | Indicator | Baseline 2016-17 | Target 2017-18 | Target Apr-June 2017 | Achievement Apr-Jun 2017 | Target Apr-Sep 2017 | Target Apr-Dec 2017 | Target 2017-18, if revised
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
A. SUGGESTIONS FOR NEW PROGRAMMES
B. SUGGESTIONS FOR ADDING CRITICAL INDICATORS
C. SUGGESTIONS FOR REMOVING CRITICAL INDICATORS

## Water Supply & sewer
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Metering and Leakage Management | A)To measure the total quantity of water consumed in the city | Total Active Consumer (In Lakh) | 21.65 | 22.25 | 22.55 | 23 | 22.71 | Total quantity of water production (in MGD) | 887 | 887 | 883 | 900 | 886 (Average of 03 Mojths ) | Due to shortage of raw water from Haryana
|  |  | Total meter connection (in LAKH) | 19.69 | 21 | 20.79 | 21.6 | 21.15 | Total Billed Quantity (in MGD) | 420.91 | 421 | 421 | 440 | 314.95 | Due to non billing of DJB installation and water emergencies target of billed quantity for April-June, 2018 could not be met out. Billing of DJB installations and water emergencies are monthly done in last quarter of the financial year
|  |  | Functional meters (in Lakh) | 14 | 16 | 14.46 | 16.5 | 14.57 | % of water lost (Non Revenue Water) | 48 | 47 | 47 | 45 | 47 | Consumers have not replaced water meter as per expectation/Target
|  | B) To Measure overall billing & collection efficiency | Demand raised through billing excluding 20 KL demand (in Cr/annum) | 1517 | 1723 | 1579 | 1680 | 464.2 | Total revenue earned excluding 20 KL subsidy (Rs. Crore/ per annum) | 1395 | 1431 | 1313. 94 | 1350 | 314.87 | Efforts will be made to achive the target in next quarter, howeveer, achivement in April-June, 2018 is in higher side in comparison of corresponding period of last year.
|  |  | Demand raised for 20 KL subsidy(in Cr/annum) | 365 | 350 | 396.66 | 425 | 92.11 | Amount of subsidy received towards 20 KL ( Rs in crore/annum) | 365 | 350 | 369.66 | 425 | 106.25 | Due to summer season, beneficiary of 20 kl subsity are less, subsity are less, therefore, demand raised against 20 KL is less than the target fixed
|  |  | Total Demand Raised (in Cr/annum) | 1882 | 2073 | 1975. 83 | 2105 | 556.31 | Total Revenue Collection | 1760 | 1781 | 1710. 60 | 1775 | 421.12 | Efforts will be made to achive the target in next quarter.
[9 empty] | % Bill collection efficiency (overall) | 80 | 80 | 86.6 | 90 | 75. 70
|  | c) installing Bulk water meteres ( Budget Announcement in Para 94) (ALSO PART OF SECTION C BUDGET SPEECH 2018-19) | SITC of electromagnetic flow meters and GPS system and inlet RTU for various Rising Mains across Delhi including 5 years Operation & Maintenance (86 Nos. Flow meters % of Physcal Progress | NA | NA | NA | 100 | 30 | % of Physcal Progress | NA | NA | NA | 100 | 30 | Specification of flow meters have been approved by the competent authority. Target date of Completion November 2018
|  |  | SITC of electromagnetic flow meters to be installed at various UGRs/tapings across rising mains of Delhi Jal Board including 5 years Operation & Maintenance (39 Nos. Flow Meters) % of Physcal Progress | NA | NA | NA | 100 | NA | % of Physcal Progress | NA | NA | NA | 100 | NA | Technical Evaluation under process. Work not awarded yet. Completion time 06 Months
|  |  | SITC of electromagnetic flow meters at various UGRs/tapings risings mains and outlet of secondary UGRs of Delhi Jal Board for secondary audit including 5 years Operation & Maintenance (2746 Nos. Flow Meters) % of Physcal Progress | NA | NA | NA | 100 | NA | % of Physcal Progress | NA | NA | NA | 100 | NA | Tender under process of award. Date of Completion - 8 Months
|  |  | Supply, Installation, Testing and Commissioning of 120 Nos. Electromagnetic flow meters % of Physcal Progress | NA | NA | NA | 100 | NA | % of Physcal Progress | NA | NA | NA | 100 | NA | NIT being reinvited due to single tender. Date of completion 06 Months
|  |  | Supply, Installation and Commissioning of 13 Nos. Electromagnetic flow meters and GPS system for West Delhi, Rohini and RWS Water mains with 05 years O&M % of Physcal Progress | NA | NA | 100 | NA | NA | % of Physcal Progress | NA | NA | 100 | NA | NA | Completed in October 2017.
2 | Water subsidy to consumers | To give free lifeline water of 20,000 litre water per month | Water subsidy given per month (Rs.in crore) | 31 | 29 | 33. 05 | 33 | 30. 07 | Average No. of beneificiaries availing water subsidy per month (in lakh) | 4.4 | 5 | 5. 18 | 6 | 4.5 | Due to summer season, beneficary of 20KL subsidy are less, therefore, target could not be met out
3 | Providing water supply in Unauthorised Colonies | a) To expand the piped water network in unauthorised colonies and reduce number of water tankers for supply of water. There are a total of 1665 unauthorised colonies in Delhi. | Length of NEW water pipeline laid in unauthorised colonies (km) | 3703 | 4053 | 3966 | 4500 | 4013 | Total number of unauthorised colonies connected to water pipeline | 1144 | 1520 | 1230 | 1521 | 1259 | 109 unauthorised colonies do not have NOC and In 35 colonies, works are not feasible
[9 empty] | % of all unauthorised colonies eligible for water supply that have access to piped water | 75 | 92 | 81 | 98 | 83
[9 empty] | Total number of metered connections provided in unauthorised colonies (Cumulative) | NA | NA | NA | NA | NA | Category tagging not available in RMS as of now
[9 empty] | Number of water tankers supplying water in unauthorised colonies (per day) | 930 | 940 | 985 | 1065 | 1046
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in unauthorised colonies | Length of water pipeline taken for replacement/ repair works (km) | 38 | 30 | 29 | 40 | 36 | % of water lost due to leakages, theft and other factors (Non Revenue Water) | 48 | 48 | 47 | 45 | 47
|  |  | Number of water samples tested for quality in unauthorised colonies | 29024 | 30000 | 24889 | 25069 | 5283 | % of samples tested that was found meeting quality standards | 95 | 97 | 97 | 97 | 97
4 | Providing water supply in rural areas | a) To expand the piped water network in rural areas (Total Rural Villages- 189) | Length of new water pipeline laid in rural areas (km)*( Cummulative) | 752 | 784 | 771 | 800 | 771. 28 | Number of households benefitted in rural villages* | NA | NA | NA | NA | NA | *This is aggregate data for Delhi. Disaggregated locality wise data will be available only from 2018-19
[9 empty] | % of rural households having access to piped water | 98 | 100 | 99 | 99 | 99
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in rural areas | Length of water pipeline taken for replacement / repair works (km) | 232 | 252 | 262 | 275 | 262.34 | Number of metered connections provided in rural areas | NA | NA | NA | NA | NA | Category tagging not available in RMS as of now
[9 empty] | % of water lost due to leakages, theft and other factors (Non Revenue Water) | 48 | 45 | 47 | 45 | 47
|  |  | Number of water samples tested for quality in rural areas | 13709 | 14000 | 14731 | 16171 | 4296 | % of samples tested that were found meeting quality standards | 95 | 95 | 96 | 97 | 97 | The acheivement is well within the permissible limit of WHO standards (95%)
5 | Augmentation of water supply in urban villages | a) To expand the piped water network in urban villages (Total Urban Villages-135) | Length of new water pipeline laid in urban villages (km)* | 395 | 399 | 396 | 400 | 397 | Number of households benefitted in urban villages* | NA | NA | NA | NA | NA | *Urban Villages are 100% covered. The tentitive 04 KMs target was kept for improvement as per requirement.
[9 empty] | % of households in urban villages having access to piped water | 100 | 100 | 100 | 100 | 100
[9 empty] | Number of metered connections provided in urban villages | NA | NA | NA | NA | NA | Category tagging not available in RMS as of now
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in urban villages | Length of water pipeline taken for replacement / repair works (km) | 190 | 194 | 190 | 193 | 191 | % of water lost due to leakages, theft and other factors (Non Revenue Water)* | 48 | 45 | 47 | 45 | 47 | *This is aggregate data for Delhi. Disaggregated locality wise data will be available only from 2018-19
|  |  | Number of water samples tested for quality in urban villages | 10701 | 12100 | 22131 | 23179 | 5863 | % of samples tested that were found meeting quality standards | 93 | 96 | 100 | 97 | 99
|  | c) Improvement of potable water to Mahipalpur and Rangpuri Villages | % of progress of construction of 6.0 ML Mahipalpur Underground Reservoir (UGR) | 0.02 | 60 | 60 | 100 | 72 | Increase in the frequency of water supply (in hours per day) | 1 | 1 | 1 | 1 | 1 | Litigation of land allotted by DDA pending in High Court
6 | Augmentation of water supply in Resettlement Colonies | a) To expand the piped water network in Resettlement Colonies (Total Resettlement Colonies- 45) | Length of new water pipeline laid in Resettlement Colonies (km)* | 652 | 655 | 653 | 657 | 653 | Number of households benefitted in Resettlement Colonies* | NA | NA | NA | NA | NA | *All RSCs are 100% covered with pipe network. The tentitive 03 KMs target was kept for improvement as per requirement. This is aggregate data for Delhi. Disaggregated locality wise data will be available only from 2018-19
[9 empty] | % of households in Resettlement Colonies having access to piped water | 100 | 100 | 100 | 100 | 100
[9 empty] | Number of metered connections provided in Resettlement Colonies | NA | NA | NA | NA | NA | Category tagging not available in RMS as of now
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in Resettlement Colonies | Length of water pipeline taken for replacement / repair works (km) | 172 | 176 | 177 | 179 | 177.5 | % of water lost due to leakages, theft and other factors (Non Revenue Water)* | 48 | 45 | 47 | 47 | 47 | *This is aggregate data for Delhi. Disaggregated locality wise data will be available only from 2018-19
|  |  | Number of water samples tested for quality in Resettlement Colonies | 10730 | 12100 | 10900 | 11000 | 2100 | % of samples tested that were found meeting quality standards | 93 | 96 | 96 | 97 | 97.5
7 | Augmentation of water supply in squatter resettlement colonies | a) To expand the piped water network in squatter re-settlement colonies and reduce number of water tankers for supply of water. There are a total of 22 squatter re-settlement colonies in Delhi. | Length of NEW water pipeline laid in squatter re-settlement colonies (km) | 45 | 60 | 51 | 118 | 76 | Total number of squatter re-settlement colonies connected to water pipeline | 2 | 6 | 3 | 8 | 8 | Water supply has been provided in 1 no Squatter resettlement colony i.e. Sardar Colony Bawana
[9 empty] | % of squatter re-settlement colonies having access to piped water | 9 | 27 | 9 | 9 | 10
[9 empty] | Number of metered connections provided in Squatter resettlement colonies | NA | NA | NA | NA | NA | 1. Disaggregated locality wise data will be available only from 2018-19 2. Category tagging not available in RMS as of now
[9 empty] | Number of water tankers supplying water in squatter re-settlement colonies (per day) | 24 | 14 | 14 | 14 | 14
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in squatter colonies | Length of water pipeline for replacement / repair works (km) | 0 | 0 | 0 | 0 | 0 | % of water lost due to leakages, theft and other factors (Non Revenue Water)* | 48 | 45 | 47 | 47 | 47 | Only New Water lines are being laid in SRCs
|  |  | Number of water samples tested for quality in squatter re-settlement colonies | 0 | 1100 | 1555 | 1656 | 337 | % of samples tested that were found meeting quality standards | NA | 95 | 100 | 97 | 95
8 | Augmentation of water supply in JJ Clusters | a) To expand the piped water network in JJ clusters and reduce number of water tankers for supply of water. There are a total of 675 JJ clusters in Delhi. | Length of new water pipeline laid in JJ clusters (km) | 31 | 49 | 31 | 50 | 31 | Number of JJ clusters provided water pipe lines | 5 | 5 | 7 | 27 | 7 | At present water supply through Public Dydrant (PWH)/tankers in JJCs. Technical feasibility exist for 364 JJCs
[9 empty] | % of households in JJ clusters having access to piped water | 0 | 0 | 0 | 0 | 0
[9 empty] | Number of metered connections provided in JJ clusters | NA | NA | NA | NA | NA | Category tagging not available in RMS as of now
[9 empty] | Number of water tankers supplying water in JJ clusters (per day) | 30 | 30 | 30 | 30 | 30
|  | b) Ongoing Operation and Maintenance (O&M) of water pipelines in JJ clusters | Length of water pipeline taken for replacement / repair works (km) | 18 | 21 | 18 | 21 | 18 | % of water lost due to leakages, theft and other factors (Non Revenue Water)* | 48 | 45 | 47 | 47 | 47
|  |  | Number of water samples tested for quality in JJ clusters | 10000 | 10000 | 9400 | 10000 | 2170 | % of samples tested that were found meeting quality standards | 96 | 96 | 97 | 97 | 98
9 | Replacement of old distribution system & strengthening of transmission network | a) To prevent water losses (through leakages), increase water pressure in pipe lines, and prevent contamination of water in rising mains (Budget Announcement- Para 99) | Length of old/defective pipeline replaced (km) | 1912 | 2064 | 2115 | 2250 | 2140 | Amount of water saved by plugging leakages in million of gallons per day (MGD) | 5 | 8 | 4 | 4 | 4
[9 empty] | % of total water supply saved from leakages | 1 | 1 | 2 | 2 | 1
|  | b) Reduction of hidden / visible leakages from Haiderpur Water Treatment Plant to Deer Park & Palam Reservoir | % of works completed in laying/replacing the water pipeline from Haiderpur WTP to Deer Park (Target - 14 km) | 0 | 50 | 50 | 90 | 62 | Amount of water saved by plugging leakages (MGD) | 1 | 2 | 3 | 5 | 3
10 | Improvement of existing water works | a) Improvement of water supply in the Mehrauli and Vasant Vihar project area by augmentation of infrastructure and replacement of 30-45 years old /damaged water lines through PPP model | % of works completed for replacement of old water lines in Mehrauli and Vasant Vihar through PPP model | 31 | 60 | 33 | 75 | 34 | % of households in command area of Mehrauli and Vasant Vihar having access to piped water (Total households - 43,000) | 81 | 90 | 81 | 90 | 81 | This is incumbent upon the road cutting permissions from land owning agencies and forest clearance.
|  |  | Water supplied in command area of Mehrauli & Vasant Vihar (in MGD) | 5 | 5.5 | 5 | 5 | 5 | Number of households benefitted from 24x7 water supply | 410 | 2000 | 410 | 6000 | 410
[9 empty] | % of water lost due to leakages, theft and other factors (Non Revenue Water) | 26 | 22 | 26 | 25 | 26
|  |  | Number of water samples tested for quality | 160 | 180 | 198 | 200 | 57 | % of samples that were tested and were found meeting quality standards | 98 | 99 | 100 | 96 | 100
|  |  | Number of complaints / grievances received from customers | 1254 | 1000 | 920 | 850 | 177 | % of complaints redressed in 24 hours | 83 | 98 | 96 | 96 | 96
|  | b) Improvement of water quality standards in Nangloi Water Treatment Plant (WTP) and its command area through PPP model | % of works completed under the overall improvement project in Nangloi Water Treatment Plant (WTP) and its command area through PPP model | 20 | 50 | 37 | 70 | 42 | % of households in command area of Nagloi having access to piped water (Total households - 180,000) | 50 | 71 | 75 | 80 | 75
[9 empty] | Number of households benefitting from 24x7 supply | 0 | 3000 | 0 | 3000 | 0
|  |  | Average water production in MGD at Nangloi WTP (capacity - 40 MGD) | 40 | 41 | 41 | 41 | 42 | % of water lost due to leakages, theft and other factors (Non Revenue Water) | 62 | 50 | 62 | 50 | 62 | Very high NRW due to unauthrized connentions in rural areas. More tankers due to fluctuation in bulk supplies & demand from elected representatives
[9 empty] | Number of water tankers supplying water in Nangloi WTP command area | 90 | 80 | 101 | 90 | 113
|  |  | Number of water samples tested for quality | 14919 | 16000 | 22174 | 23000 | 6365 | % of samples that were tested and were found meeting quality standards | 94 | 98 | 98 | 98 | 98
| \\ |  | Number of complaints/ grievances received from customers | 32911 | 30000 | 29517 | 28000 | 6329 | % of complaints redressed in 24 hours | 40 | 55 | 50 | 55 | 54
11 | Ranney wells & Tube wells | To augment the availability of water through addition and rehabilitation of tube wells and Ranney Wells | Number of tube wells added | 4000 | 4072 | 4040 | 4100 | 4047 | Amount of water extracted from Ranney wells & tube wells (MGD) | 80 | 81 | 81 | 86 | 81
|  |  | Number of tube wells redeveloped | 281 | 379 | 346 | 400 | 351
|  |  | Number of Ranney wells added | 0 | 0 | 0 | 0 | 0
|  |  | Number of Ranney wells redeveloped | 4 | 7 | 4 | 0 | NA | [6 empty] | No Ranney Wells is to be redevloped in 2018
[9 empty] | Number of households benefitted | 530000 | 613000 | 600000 | 586000 | 514215 | This is aggregate data for Delhi
12 | Distribution Mains and Reservoirs | a) Pilot Project for improving efficiency of water distribution network and reduction in NRW and providing network in the entire command area of Malviya Nagar UGR | % of works completed under the overall project of improving efficiency of water distribution network and reduction in NRW and providing network in the entire command area of Malviya Nagar UGR | 53 | 85 | 78 | 100 | 79 | % of households in command area of Malviya Nagar having access to piped water (Total households - 45000) | 84 | 98 | 85 | 100 | 85 | Slow progress due to permission. This will be subject to NOC from forest/UD for U/A col. In addition, slow progress due to RR permissions from SDMC.
[9 empty] | Number of household benefitting from 24x7 supply | 760 | 5000 | 760 | 10000 | 760
[9 empty] | % of water lost due to leakages, theft and other factors (Non Revenue Water) | 44 | 38 | 38 | 36 | 36
[9 empty] | Number of water tankers supplying water | 4 | 3 | 4 | 3 | 4
|  |  | Number of water samples tested for quality | 1800 | 2000 | 2150 | 2200 | 560 | % of samples that were tested and were found meeting quality standards | 94 | 97 | 97 | 97 | 97
|  |  | Number of complaints / grievances received from customers | 32911 | 30000 | 26103 | 25000 | 9232 | % of complaints redressed in 24 hours | 47 | 70 | 70 | 72 | 72 | Increased complaints due to fluctuations in bulk supplies
|  | b) To improve the storage capacity for equitable distribution of water supply by construction of 3 UGRs at Karala, Mangolpuri & Mangolpur Kalan | Length of water pipeline laid/replaced (in KM) | 52 | 70 | 70 | 71 | 71 | Improvement in average water supply hours (hours per day) | 2 | 4 | 4 | 4 | 4 | UGR and BPS of Y block mangolpuri completed and ready for commisssioning
[9 empty] | Number of households benefitted | 30000 | 40000 | 38000 | 38000 | 38000
|  |  | Number of UGRs newly commissioned | 0 | 3 | 2 | 3 | 2 | Number of colonies to be under command area of Karala Mangolpuri Y-Block and Mangol pur Kalan UGR | 0 | 28 | 13 | 28 | 13 | 28 unauthorized colonies and Mangolpur kala village, Sultanpuri resettlement colonies
|  | c) To improve the storage capacity for equitable distribution of water supply by construction of UGRs at Maya Puri and Sonia Vihar (Budget Announcement para No. 100) | Length of water pipeline laid/replaced (in KM) | 1.2 | 6 | 6 | 18 | 10 | Improvement in average water supply hours (hours per day) | 0 | 0 | 0 | 4 | 0 | Targets will be acheived after completion of UGRs
[9 empty] | Number of households benefitted | 0 | 0 | 0 | 140000 | 0
|  |  | Number of UGRs newly commissioned | 0 | 0 | 0 | 1 | 0 | Number of colonies to be under command area of Karala Mangolpuri Y-Block and Mangol pur Kalan UGR | 0 | 0 | 0 | 28 | 0 | Mayapuri UGR to be commissioned by 31st March 2019.
|  | d) To improve the storage capacity for equitable distribution of water supply by construction of 02 UGRs at Najafgarh and Mundka | Length of water pipeline laid/replaced (in KM)-Najafgarh B UGR | 20 | 55 | 53 | 74 | 65 | Improvement in average water supply hours (hours per day)-Najafgarh B | 0 | 2 | 1 | 4 | 3
|  | (Budget Announcement para no100) | [6 empty] | Number of households benefitted-Najafgarh B | 0 | 1500 | 1000 | 30000 | 1500
[9 empty] | Number of colonies to be under command area of Najafgarh B | 0 | 2 | 2 | 90 | 2
|  |  | Length of water pipeline laid / replaced (in KM)-Mundka UGR | 1.4 | 9 | 8.4 | 15.2 | 15 | Improvement in average water supply hours (hours per day)-Mundka | 0 | 0 | 0 | 4 | 2
[9 empty] | Number of households benefitted-Mundka | 0 | 0 | 0 | 20000 | 800
[9 empty] | Number of colonies to be under command area of Mundka | 0 | 0 | 0 | 20 | 1
|  |  | Number of New UGRs to be commissioned | 0 | 0 | 0 | 2 | 0 | [6 empty] | Work in Progress Najafgarh-B, 70%, Mundka-50%
13 | Raw Water Mains | Providing Amonia free Raw water from DSB canal to Haiderpur and Chandrawal WTP | Providing and laying 2400 MM dia MS gravity main from DSB canal to Haiderpur and Chandrawal WTP % of physical progress | 0 | 0 | 0 | 25 | 0 | Length of raw water main to provide amonia free raw water at wazirabad and chandrawal WTP (in Kms) | 0 | 0 | 0 | 2 | 0 | Tenders invited and are due on 23.5.2018 and work is likely to start after rainny season
14 | Sewerage Treatment Plants (STP), Sewerage Pumping Stations (SPS) & Rising mains | a) Operation and maintenance (O&M) of existing STPs | Number of existing STPs | 32 | 32 | 32 | 32 | 32 | % of installed capacity of STPs that is currently under use | 74 | 90 | 76 | 90 | 76 | 460 MGD of sewerage is being treated against the installed capacity of 607 MGD (76%). Target of 90% will be acheived after commissioning of ISP project
|  |  | Total installed capacity of existing STPs (MGD) | 607 | 606 | 607 | 607 | 607
|  |  | Number of existing STPs undergoing rehabilitation of infrastructure | 1 | 1 | 0 | 0 | 0 | % STPs where BOD of treated effluent is under 10ppm | 25 | 25 | 25 | 25 | 25
[9 empty] | % STPs whose TSS of treated effluent is under 10ppm | 19 | 19 | 19 | 19 | 19 | 6 nos STPs out of total 32 nos .
[9 empty] | Total sewerage generated in Delhi (MGD) | 703 | 720 | 720 | 720 | 720 | Estimates based on 80 % of total water supply of 900 MGD present
[9 empty] | Sewerage generated in Delhi that goes to River Yamuna untreated (MGD) | 266 | 180 | 260 | 110 | 258 | treatment is 460 MGD out of total 720 MGD of waste water generated.
|  | b) Improvement and augmentation of sewerage network | Number of new STPs under construction | 2 | 17 | 17 | 17 | 17 | % of total sewerage that goes to River Yamuna untreated | 37 | 25 | 36 | 15 | 36 | Baseline- STPs at Nilothi & Pappan Kalan (2 nos). New STP at Corronation Piller and 14 STPs in Najafgarh areas (15 nos) STPs at Nilothi & Pappan Kalan.
|  |  | Number of STPs with more than 50% construction completed | 2 | 2 | 2 | 2 | 2
|  |  | Number of new STPs with 100% construction completed and facility operationalised | 0 | 2 | 0 | 0 | 0
|  |  | Total capacity of STPs under construction (MGD) | 40 | 149 | 149 | 149 | 149 | [6 empty] | Nilothi 20 MGD, Pappan Kalan 20 MGD, Coronation Piller 70 MGD, 14 STPs in Najafgarh area 39 MGD. Total 149 MGD
|  |  | Additional treatment capacity added due to newly commissioned STPs (MGD) | 40 | 0 | 0 | 0 | 0
|  |  | Number of SPSs to be newly commissioned | 0 | 1 | 0 | 1 | 1 | [6 empty] | Kalyan puri SPS fully commissined by June 2018
|  |  | Length of Rising mains to be laid under this project (in Km) | 0 | 7.85 | 2.5 | 10 | 2.5 | [6 empty] | 4 projects of rising mains at Haiderpuri SPS, Nangloi SPS, Dwarka water body and at Mandawali SPS.
15 | Jawaharlal Nehru National Urban Renewal Mission (JnNURM) projects | a) To reduce pollution in River Yamuna by construction of 20 MGD Nilothi STP at Ph-II- and 20 MGD STP at Pappankalan Ph-II | % of works completed of STPs at Nilothi & Papankalan | 98 | 100 | 99 | 100 | 100 | Total capacity of newly commissioned STPs at Nilothi and Papankalan (MGD) | 40 | 40 | 40 | 40 | 40
[9 empty] | Power generated from sewage plants (kWh/day) | 0 | 24000 | 10000 | 24000
|  |  | Time line for commissioning of STPs at Nilothi and Pappankalan | 30.04.2016 | 31.03.2018 | 30.04.2016 | 31.12.2018 | [7 empty] | Pappankalan Plant is likely to be fully commissioned by June, 2018 and Nilothi plant by December , 2018.
|  | b) Laying of Interceptor Sewer along 03 major drains viz Najafgarh, Supplementary and Shahdara for abetment of population in Yamuna under JnNURM project. | Total length of interceptor sewer laid (km) | 46 | 55 | 48 | 53 | 49 | Total flow of Sewage trapped for treatment at various STPs (in MGD) | 82 | 242 | 92 | 150 | 99 | Target of 242 MGD will be achieved after commissioning of ISP project by end of 2018.
16 | Sewerage facilities in Unauthorised Colonies | a)To provide sewer facility in unauthorised colonies. There are a total of 1639 unauthorised colonies in Delhi. (Budget Announcement- Para 97) | Length of NEW sewer line laid in unauthorised colonies (km) | 1600 | 1800 | 1840 | 2290 | 90 | Total number of unauthorised colonies connected to sewerage network | 241 | 300 | 269 | 520 | 269 | Works of laying of sewer line have been completed in about 70 colonies.
[9 empty] | % of all eligible unauthorised colonies that are provided with sewerage facilities | 15 | 19 | 17 | 34 | 17 | Total eligible colonies = 1665-109-34=1522 nos. Sewerage facility provided in 263 out of 1522 eligible ( 17.3%)
[9 empty] | Total number of households connected to sewerage network (Cumulative) | 240000 | 304000 | 270000 | 520000 | 270000
|  | b) Instalation of Small STPs ( Budget Announcement in Para 95) (ALSO PART OF SECTION BUDGET SPEECH 2018-19) | Decentralization of STPs & sewerage system in Burari area % of Physcal Progress | 0 | 0 | 0 | 25 | 0 | [6 empty] | Under Burari Project, 07 decentralized STPs shall be constructed and 86 KMs sewer lines shall be laid.
|  |  | Decentralization of STPs & Sewerage system in Chattarpur area % of Physcal Progress | 0 | 0 | 0 | 15 | 0 | [6 empty] | Under chattarpur Project 09 decentralized STPs shall be constructed and 147 KMs sewer lines shall be laid
|  |  | Decentralization of STPs & Sewerage system in Kirari area % of Physcal Progress | 0 | 0 | 0 | 15 | 0
|  |  | Decentralization of STPs & Sewerage system in Narela, Zindpur and Palla area % of Physcal Progress | 0 | 0 | 0 | 15 | 0 | [6 empty] | The number and capacity of decentralozed STPs in zindpur and palla area will depend upon the total no. of locations of land available.
|  |  | Decentralization of STPs & Sewerage system in Bawana and Kanjhawala area % of Physcal Progress | 0 | 0 | 0 | 15 | 0
|  |  | Decentralization of STPs & Sewerage system in Badarpur area % of Physcal Progress | 0 | 0 | 0 | 15 | 0 | [6 empty] | 01 decentralized STPs shall be constructed and 234 KMs sewer lines shall be laid.
|  |  | Decentralization of STPs & Sewerage system in Mundka (Part) area % of Physcal Progress | 0 | 0 | 0 | 15 | 0
|  |  | STPs in Najafgarh Area (Capacity of the STPs shall be finalized after actual flow measurements in the command area) | 0 | 0 | 0 | 15 | 0 | [6 empty] | Works for 14 STPs awarded. Land under acquisition. Internal sewer lines to be awarded.
17 | Sewerage facilities in Rural Villages | Providing sewerage facilities in the command area of Ghitorni WWTP (Internal & peripheral sewer) | Length of new sewer line laid in rural villages (km)* | 36 | 38 | 38 | 0 | 0 | Total number of rural villages connected to sewerage network | 54 | 55 | 55 | 0 |  | There are a total of 189 rural villages in Delhi. The balance villages will be covered under schemes of decentralized STPs.
[9 empty] | % of all rural villages provided with sewerage facilities | 28.6 | 29.1 | 29.1 | NA
[9 empty] | Number of households newly connected to sewerage network | 500 | 520 | 520 | NA
18 | Sewerage facilities in Regularised Unauthorised colonies | Up-keep and maintenance of the existing sewerage system by replacing, laying and desilting of sewer line | Length of new sewer line laid in replacement of old/defective line (in KM) | 845 | 900 | 873 | 950 | 887 | Number of regularized un-authorised colonies where new sewer line repaired | NA | NA | 20 | 20 |  | This is aggregate data
|  |  | Length of sewer line where desilting activities conducted | NA | 400 | 1711 | 3200 | 1450
19 | Trunk, Peripherals, Sewer and Gravity Duct | a) Construction of new trunk /peripheral sewer lines | Length of new trunk /peripheral sewers to be laid (Km) | 6 | 8.5 | 7 | 9.5 | 7 | Plant capacity under use at Yamuna Vihar STP in MGD (Installed capacity -135) | 16 | 22 | 18 | 35 | 18 | Project of trunk sewer at Gokul Pur and Karawal Nagar is in progress. Around 20 MGD sewerage will trapped through Interceptor sewer.
|  | b) Rehabilitation of trunk/peripheral sewer lines (Budget Announcement- Para 96) | Rehabilitation of trunk /peripheral sewers (Km) | 135 | 175 | 136 | 190 | 139 | Plant capacity under use at Rithala and Keshopur STP in MGD, Okhla, Vasant Kunj(Installed capacity - 277 MGD) | 236 | 263 | 236 | 263 | 236 | 6 projects of sewer rehabilitation of peripheral sewer being undertaken out of which 3 projects are under NGT monitoring. Installed capacity at Rithala- 80 MGD, Keshopur-72 MGD, Okhla-140 MGD, Vasant Kunj-5 MGD.
20 | National River Conservation Programme (Yamuna Action Plan (YAP)-III) | To reduce the pollution in River Yamuna by rehabilitation /upgrading STPs and rehabilitation of Trunk sewer / rising mains in the command area of Kondli, Okhla and Rithala STPs | % of construction/ rehabilitation of 3 STPs | 0 | 0 | 0 | 0 | 0 | Reduction in pollution (BOD load) due to sewerage into Yamuna (In MGD ) | 0 | 0 | 0 | 0 | 0 | Following 3 STPs to be taken up: Kondli, Okhla, Rithala. The projects will be commissioned by Dec'2020. Out of total 32 nos, 8 nos i.e. Rithala- 1 No, Kondli- 3 Nos and Okhla -4 Nos STPs are to be rehabilated under YAP-III.
|  |  | Length of trunk sewers rehabilitated (km) | 0 | 5 | 0 | 7 | 0 | Reduction in untreated sewage draining in the Yamuna (MGD) | 0 | 4 | 0 | 8 | 0 | After completion of the project, 16 MGD untreated sewage will be captured for treatment. Two works have been awarded and are in progress.
|  |  | Length of rising mains rehabilitated (km) | 0 | 0 | 0 | 5 | 0
8 | Rejuvenation of River Yamuna | To build capacity within organization and treat the entire hydrology of Yamuna River | Total number of drains cleaned (Target - 144) | 0 | 1 | 0 | 0 |  |  | 0 | 1 |  |  |  | Drains are being developed by I & F department. DJB is providing technical assistance. One water body at Rajokari is being Rejuvenated by I&FC Deptt.
|  |  | Total number of water bodies where cleaning and development works completed (Target - 93) | 0 | 4 | 0 | 0 |  | Development of recreational space with clean water bodies (in Sq.km.) | 0 | 0 | 0 | 0
21 | Urgent & Emergent works in Water supply and Sanitation (Rs.7000 Lakh) (capital) | Carry out development work in each Assembly Constituency on the recommendation of Hon'ble MLAs | Number of projects newly sanctioned | [11 empty] | This is a new scheme being processed with the consent of area MLAs. The budget allocation is being done. As such, the parameters will be indicated in the next quarter.
Number of projects where construction work started
|  |  | Number of projects where works completed | [5 empty] | % of projects completed within prescribed time line as per work order
% of projects where Third Party Quality (TPQ) control done
% of projects found satisfactory in TPQ control