## 137 - 143 Part-C
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Aam Aadmi Mohalla Clinic [Rs.150.00 Crore] | Provisions of Primary Health Care | Identification of sites | 451 | 530 | 721 | 530
|  |  | Allotment of Sites/Permission from Land Owning agencies (530 sites) |  | NA | 614 | 665
|  |  | Joint Survey by PWD and CDMOs |  | 30/04/2018 | completed | completed | [5 empty] | 390 sites found feasible.
|  |  | Construction by PWD |  | 2018-10-31 | 5 | 146 | [5 empty] | 290sites physically handed over to pwd out of which 146 are under constuction
|  |  | Provision of Water & Power |  | 2018-10-31 | 1900-01-04 | _ | [5 empty] | *will be placed after installation of porta cabin
|  |  | Number of AAMC handed over by PWD to the Department |  | 530 | 1900-02-08 | 146
2 | 600 bedded Hospital at Ambedkar Nagar Date of approval by EFC-26.7.16 Sanctioned Cost Rs.180.95 Crore. No. of Beds : 600 (DHS Capital-Rs. 20 crore) | To set up new Hospitals | Date of award of Work | 30-10-2013 | 100 | 98 | 100 | Date & Month of start of the Hospital | NA | NA | NA | NR | Sanction cost Rs.180.95 Crore. No. of Beds:600 subject to payment of Rs.800 Crores from DGHS to BSES for electricity connection.
|  |  | Date by which Hospital will be made functional | 73% | # | NR
|  |  | Physical Progress (%) | -- | 100 | 98 | 100 |  | -- | -- | -- | -- | Works related to testing/ commissioning pending.
|  |  | Date of Completion | 03-02-2019 | 03-02-2019 | -- | 100 |  | -- | -- | -- | -- | Testing and commissioning work shall be started after BSES connection which is pending due to payment to be released by DGHS.
3 | 768 bedded Hospital at Burari Date of approval by EFC-29.11.18 Sanctioned Cost Rs.265.80 Crore. No. of Beds : 768 (Covered under Total B.E. 2019-20- Rs. 188 crore for C/o new hospitals) | To set up new Hospitals | Date of award of Work | -- | -- | -- | -- | Date & Month of start of the Hospital | -- | -- | -- | -- | Total B.E. 2019-20-Rs. 188.00 crore for c/o new hospitals.
|  |  | Date by which Hospital will be made functional | 73% | # | NR
|  |  | Physical Progress (%) | 70 | 80 | 80 | 100
|  |  | Date of Completion | - | - | - | 30-11-2019
4 | 6200 new beds will be added in 10 existing Delhi Government Hospitals. Total B.E. 2019-20 Rs. 400.00 crore | To add new beds
(i) | Bhagwan Mahavir | 444 | Date of Award of Work | NR | NR | NR
Physical Progress (%)
Date by which new beds will be made functional
(ii) | Acharya Shree Bhikshu | 270 | Date of Award of Work | NR | NR | NR
Physical Progress (%)
Date by which new beds will be made functional
(i) | Dr. Baba Saheb Ambedkar Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.194.91 Crore. No. of Beds : 400 | Construction of a new mother & Child Block screening OPD | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Block | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | NA
|  |  | Date by which new beds will be made functional | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2021-09-01
(ii) | Deep Chand Bandhu Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.69.36 Crore. No. of Beds : 200 | To add new beds | Date of Award of Work |  |  |  | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | NR | NR | NR
Date by which new beds will be made functional
|  |  | Physical Progress (%) | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-06-01
(iii) | Rao Tulla Ram Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.86.31 Crore. No. of Beds : 258 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | --
|  |  | Date by which new beds will be made functional | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-06-01
(iv) | Guru Govind Singh Govt. Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.172.03 Crore. No. of Beds : 470 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | --
|  |  | Date by which new beds will be made functional | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2021-09-01
(v) | Sanjay Gandhi Memorial Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.117.78 Crore. No. of Beds : 386 | Construction of Trauma Centre and Utility Block | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Trauma Centre & Utility Block | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | --
|  |  | Date by which new beds will be made functional | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2021-04-01
(vi) | Acharaya Shri Bhikshu Govt. Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.94.38 Crore. No. of Beds : 376 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-06-01 | [5 empty] | 15 months from date of approval
(vii) | Aruna Asaf Ali Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.55.36 Crore. No. of Beds : 51 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-06-01
(viii) | Bhagwan Mahavir Govt. Hospital Date of approval by EFC-06.02.18 Sanctioned Cost Rs.172.79 Crore. No. of Beds : 477 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-03-31 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-09-01
(ix) | Sri Dada Dev Shishu Maitri Chikitsalaya Date of approval by EFC-11.01.19 Sanctioned Cost Rs.53.44 Crore. No. of Beds : 175 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-05-01 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-08-01
(x) | Construction of new Mother & Child Hospital, Khichripur Date of approval by EFC-29.11.18 Sanctioned Cost Rs.143.73 Crore. No. of Beds : 460 | To add new beds | Date of Award of Work | -- | -- | -- | 2019-02-01 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | NR
|  |  | Date of Completion | -- | -- | -- | --
(xi) | Addition remodelling of SRCH at Narela Date of approval by EFC-11.01.19 Sanctioned Cost Rs.244.35 Crore. No. of Beds : 773 |  | Date of Award of Work | -- | -- | -- | 2019-05-01 | Date & Month of start of the Hospital | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2022-02-01
(xii) | Remodelling of JPCH at Shastri Park Date of approval by EFC-11.01.19 Sanctioned Cost Rs.189.77 Crore. No. of Beds : 221 |  | Date of Award of Work | -- | -- | -- | 2019-05-01 | Date & Month of start of the Hospital | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2021-09-01
(xiii) | Expansion & Remodelling of existing casualty block of LNH Date of approval by EFC-08.3.19 Sanctioned Cost Rs.58.71Crore. No. of Beds : 383 |  | Date of Award of Work | -- | -- | -- | 2019-07-01 | Date & Month of start of the Hospital | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-12-01
(xiv) | C/o New block for Medicine, Mother, & Peadiatric Centre at LNH Date of approval by EFC-08.3.19 Sanctioned Cost Rs.533.91 Crore. No. of Beds : 1570 |  | Date of Award of Work | -- | -- | -- | 2019-10-01 | Date & Month of start of the Hospital | -- | -- | -- | --
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2022-09-01
5 | Indira Gandhi Hospital at Sec-9, Dwarka (Covered under Total B.E. 2019-20 -Rs. 188 crore for C/o new hospitals) | To provide super-specialty health facility for general public. The hospital is under construction with revised plan of 1241 beds. | Date of Award of Work | 28-08-2014 | -- | -- | -- | Date & Month of start of the Hospital | -- | -- | -- | NA | Status for approval of revised cost for 1241 beds is not clear)
|  |  | Physical Progress (%) | -- | 85 | 80 | 100
|  |  | Date of Completion | -- | -- | -- | 31-03-2020
6 | Construction of MAIDS Phase -II | To provide better health facility to general public | Construction work completed (%) | 84 | 100 | 99.4 | 100 | Dental chair | -- | -- | -- | 250
|  |  | Date of Completion | -- | -- | -- | -- | Bed capacity of the hospital | -- | -- | -- | 35
7 | Remodelling of 94 Delhi Govt. Dispensaries at different districts of Delhi into Polyclinics (Phase-I & II) Date of approval by EFC-07.02.18 Sanctioned Cost Rs.170.30Crore. Phase-I-Rs. 91.63 crore Phase-II-Rs. 78.67 crore |  | Date of Award of Work | 28-08-2014 | -- | -- | 2019-03-01 | Date & Month of start of the Hospital | -- | -- | -- | NA
|  |  | Physical Progress (%) | -- | -- | -- | --
|  |  | Date of Completion | -- | -- | -- | 2020-12-01
8 | Construction of ILBS-Phase II Hospital Date of approval by EFC-26.7.16 Sanctioned Cost Rs.497.22Crore. |  | Date of Award of Work | -- | -- | -- | -- | Date & Month of start of the Phase-II | -- | -- | -- | -- | Project is 16moths behind the schedule.
|  |  | Physical Progress (%) | -- | -- | -- | 98%
|  |  | Date of Completion | -- | -- | -- | 2019-04-01