## Final
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Major Drainage (a) Procurement of heavy machinery for desilting of drains (Rs.300 Lakhs) (Capital) | Desilting of drains | Date of Procurement of new machinery. |  | 43452 | 43452 | 43921
|  |  | Total number of machines procured and made operational | 46 | 53 | 53 | 59
|  |  | Total length of drains (km) desilted using machinery | 400 | 400 | 400 | 382 | Quantity of silt disposed at SLF site (in Lakhs MT) | 1.27 | 1.5 | 0.9 | 1.16 | CRRI delhi has been appointed consultant in I&FC Department for usage of desilted earth from the drains. A draft report has been received from CRRI and the same circulated to all division of I&FC Department and other agencies for feed back/comments.
|  |  | Total production of silt (in Lakhs MT) | 4.29 | 4.5 | 6 | 4.84 | Quantity of silt disposed at banks as well in depression (in Lakhs MT) | 3.02 | 3 | 5.1 | 3.68
|  |  | Number of staff engaged in desilting | 167 | 167 | 167 | 167 | Silt used in productive activity | 0 | 0 | 0 | 0
| (b) Embankment/ Major Drainage Schemes (Rs. 500 Lakhs) (Capital) | Protection, widening, strengthening and resurfacing of embankments. | Number of projects including ongoing projects of previous years | 3 | 1 | 1 | 1 | % age of ONGOING projects that are within deadline as per Work Order | 0 | 100 | 0 | 100 | Water supply pipeline is being laid by DJB along RME. After laying of pipeline by DJB, the work shall be takenup.
|  |  | Number of projects for which construction has started/in progress | 3 | 1 | 1 | 1 | % age of projects COMPLETED within deadline as per Work Order | 0 | 100 | 0 | 100
|  |  | Number of projects for which construction is fully completed | 2 | 1 | 0 | 1 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 100
2 | Other Drainage Works (Rs. 6000 Lakhs) (Capital) | (a) Remodeling / Improvement of Existing Drains | Number of projects including ongoing projects of previous years | 5 | 6 | 6 | 15 | % age of ONGOING projects that are within deadline as per Work Order | 40 | 100 | 50 | 100 | (1) Delay due to monsoon seasons. (2) Land dispute with Haryana Irrigation. (3) Land dispute with UP Irrigation. (4) Shifting of electric poles by BSES.
|  |  | Number of projects for which construction has started/in progress | 5 | 6 | 6 | 15 | % age of projects COMPLETED within deadline as per Work Order | 40 | 100 | 0 | 100
|  |  | Number of projects for which construction is fully completed | 2 | 5 | 2 | 10 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  |  | Length of projects which have been completed (in kms) | 6.3 | 9.39 | 8.9 | 35.7
|  | (b) Remodelling of Najafgarh Pond Drain by constructing R.C.C. Reaining wall from RD 600m to RD 1942m. | Date of Tender floating | NA | NA | 16.07.2018 | [6 empty] | Work could not be started as Tre cutting permission awaited from Forest Department.
|  |  | Date of work award | NA | NA | 23.02.2019
|  |  | Date of Start of work | NA | NA | 02.03.2019
|  |  | Date of completion of work | NA | NA | NA | 29.02.2020
|  |  | Percentage of work completed | NA | NA | 0 | 100
|  | (c) Access Roads and Bridge related projects Construction of bridges/ roads/ resurfacing or improvement of roads on the banks of embankments/ banks of drains. | Number of projects including ongoing projects of previous years | 24 | 20 | 20 | 33 | % age of ONGOING projects that are within deadline as per Work Order | 8 | 100 | 40 | 100 | Delay due to (1) Monsoon season (2) land dispute (3) Failure of test pile and redesigning of foundation (4) Change in alignment and shifting of transformer (5) Shifting of pipeline by DJB.
|  |  | Number of projects for which construction has started/in progress | 24 | 20 | 20 | 33 | % age of projects COMPLETED within deadline as per Work Order | 8 | 100 | 0 | 100
|  |  | Number of projects for which construction is fully completed | 13 | 16 | 7 | 20 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  | (d) Construction of four lane R.C.C. Bridge at upstream of RD 20180m (existing Dhoolsiras Bridge) on Najafgarh Drain | Date of Tender floating |  |  | 06.02.2019 | 27.05.19 | [5 empty] | The tender of the work was rejected by the competent authority and to be retendered after modal code of conduct.
|  |  | Date of work award |  |  |  | 27.07.19
|  |  | Date of Start of work |  |  |  | 12.08.19
|  |  | Date of completion of work |  |  |  | 11.08.20
|  |  | Percentage of work completed |  |  |  | 30
|  | (e) Construction of four lane R.C.C. Bridge at upstream of RD 14468m (existing Badusarai Bridge) on Najafgarh Drain | Date of Tender floating |  |  | 06.02.2019 | 27.05.19 | [5 empty] | The tender of the work was rejected by the competent authority and to be retendered after modal code of conduct.
|  |  | Date of work award |  |  |  | 27.07.19
|  |  | Date of Start of work |  |  |  | 12.08.19
|  |  | Date of completion of work |  |  |  | 11.08.20
|  |  | Percentage of work completed |  |  |  | 50
|  | (f) Construction of six lane R.C.C. Bridge on downstream of existing bridge on Chhawla Najafgarh Road. | Date of Tender floating |  |  | 08.02.2019 | - | [5 empty] | Submitted for acceptance of tender by competent authority.
|  |  | Date of work award |  |  |  | 27.05.19
|  |  | Date of Start of work |  |  |  | 11.06.19
|  |  | Date of completion of work |  |  |  | 10.06.20
|  |  | Percentage of work completed |  |  |  | 25
|  | (g) Works related to protection of Govt land. Construction of walls for protection of Govt. Land from encroachment. | Number of projects including ongoing projects of previous years | 8 | 2 | 2 | 7 | % age of ONGOING projects that are within deadline as per Work Order | 38 | 100 | 50 | 100
|  |  | Number of projects for which construction has started/in progress | 8 | 2 | 2 | 7 | % age of projects COMPLETED within deadline as per Work Order | 38 | 100 | 100 | 100
|  |  | Number of projects for which construction is fully completed | 6 | 2 | 1 | 7 | Number of projects where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  |  | Length of projects which have been completed (in kms) | 12.36 | 14.2 | 4.9 | 20.98
3 | Development of Chhat ghats (Rs. 2000 Lakhs) (Capital) | Construction of Chhat ghats for Chhat Puja all over Delhi | Number of permanent Chhat ghats constructed | 25 | 31 | 31 | 37 | % age of projects COMPLETED within deadline as per Work Order | 100 | 100 | 100 | 100
|  |  | Number of temporary Chhat ghats constructed | 349 | 349 | 593 | 593 | % age of projects COMPLETED within deadline as per Work Order | 100 | 100 | 100 | 100
4 | Rejuvnation/ maintenance & preservation of water bodies (Rs. 2500 Lakhs) (Capital) | Rejuvenation of water bodies | Number of water bodies including ongoing projects of previous years |  |  |  | 95 | % age of ONGOING water bodies that are within deadline as per Work Order |  |  |  | 100 | Consultant have been appointed for 60 water bodies in which DPR of 22 nos. have already been received and rest will be received in phases by 31.07.2019 and the remaining 35 water bodies preliminary estimate for A/A & E/S have been prepared and the same are being placed in 42nd TAC meeting.
|  |  | Number of water bodies for which construction has started/in progress |  |  |  | 48 | % age of water bodies COMPLETED within deadline as per Work Order |  |  |  | 100
|  |  | Number of water bodies for which construction is fully completed |  |  |  | 20 | Number of water bodies where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  |  | Percentage of work completed |  |  |  | 25
5 | Rejuvnation of Drains (Rs. 10000 Lakhs) (Capital) | (A) Rejuvenation of drains | Number of drains including ongoing projects of previous years |  |  |  | 27 | % age of ONGOING drains that are within deadline as per Work Order |  |  |  | 100 | Consultants have been appointed for 27 Nos. drains in which DPR have been received for 05 Nos. and 22 Nos. drains DPR are expected to be received by 30.10.2019.
|  |  | Number of drains for which construction has started/in progress |  |  |  | 10 | % age of drains COMPLETED within deadline as per Work Order |  |  |  | 100
|  |  | Number of drains for which construction is fully completed |  |  |  | 2 | Number of drains where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  |  | % of physical work completed |  |  |  | 7 | Total length of Drainsthat rejuvented (In Km) |  |  |  | 18.73
|  | (B) Rejuvenation of Minors | Number of Minors including ongoing projects of previous years |  |  |  | 5 | % age of ONGOING Minors that are within deadline as per Work Order |  |  |  | 100 | Consultants have been appointed for 5 Nos. minors and DPR have been received for 05 Nos. minors on 27.02.2019 which are under scrutiny.
|  |  | Number of Minors for which construction has started/in progress |  |  |  | 5 | % age of Minors COMPLETED within deadline as per Work Order |  |  |  | 100
|  |  | Number of Minors for which construction is fully completed |  |  |  | 1 | Number of Minors where penalty imposed on the contractor due to delay in completion. | 0 | 0 | 0 | 0
|  |  | % of physical work completed |  |  |  | 5 | Total length of Minors that rejuvented (In Km) |  |  |  | 3.4
|  | (C) Construction of shallow reservior in Yamuna Flood Plain from Palla to Wazirabad. | Date of appointment of consultant |  |  | 08.03.2019
|  |  | Date of appointment of consultant |  |  | 08.03.2019 | NA | [5 empty] | Work can be taken up only after approval from EFC and receipt of NOC from Haryana Irrigation Department. Consultant have been appointed and DPR are to be received, however, before taking up the work approval of Upper Yamuna Board, CWC, Stake Holder States like Haryana, U.P. and clearance from HOn'ble NGT is required.
|  |  | Date of receipt of DPR |  |  |  | 10.07.2019
|  |  | Date of Tender floating |  |  |  | 01.01.2020
|  |  | Date of work award |  |  |  | 15.02.2020
|  |  | Date of Start of work |  |  |  | 15.03.2020
|  |  | Date of completion of work |  |  |  | 31.12.2020
|  |  | Percentage of work completed |  |  |  | 5